Northbeam DESIGN

Northbeam Barcelona

Fee Proposal

Diagonal Norte - office refurbishment and extension

Prepared for: Inmobiliaria Diagonal Norte S.L.

Location: Barcelona, Spain

Reference: NBS-BCN-2024-006

Date: 2024-05-07

Validity: 90 days from the date of issue

# 1. Project Understanding

Inmobiliaria Diagonal Norte S.L. has invited Northbeam Studio to submit a fee proposal for Diagonal Norte - office refurbishment and extension, located in Barcelona, Spain. The proposal covers Architecture, Interior Design services from Concept Design to Design Development.

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 18,500 m² |
| Site area | 3,100 m² |
| Interior design area | 14,000 m² |
| Site considerations | Protected heritage facade retained; constrained urban site |

# 2. Scope of Services

## 2.1 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Scheme Design (Anteproyecto): Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

Design Development: Fully coordinated design development drawings; facade and envelope details; key interior architecture details; outline specifications; design development report to support the local architect of record.

## 2.2 Interior Design

Concept Design: Interior design concept and mood boards for public areas and key typical spaces; space planning; concept presentation.

Scheme Design (Anteproyecto): Developed layouts, reflected ceiling plans, key elevations and finishes palette; preliminary FF&E strategy.

Design Development: Detailed interior drawings for public areas and typical rooms or units; finishes schedule; FF&E design intent package.

# 3. Deliverables

- Design report and drawings per stage: 3

- Rendered images: 8

- Client presentations: 4

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Scheme Design (Anteproyecto) | 8 weeks |
| Design Development | 12 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in EUR and exclude VAT or other applicable taxes.

| Service | Stage | Fee (EUR) |
| --- | --- | --- |
| Architecture | Concept Design | 218,000 |
| Architecture | Scheme Design (Anteproyecto) | 218,000 |
| Architecture | Design Development | 290,500 |
| Interior Design | Concept Design | 107,500 |
| Interior Design | Scheme Design (Anteproyecto) | 107,500 |
| Interior Design | Design Development | 143,500 |
|  | Total professional fee | 1,085,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (EUR) | Amount (EUR) |
| --- | --- | --- | --- |
| Rendered images | 8 | 1,850 | 14,800 |

Marketing-quality still images

# 7. Payment Schedule

| No. | Milestone | Share | Amount (EUR) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 108,500 |
| 2 | On approval of Concept Design | 27% | 292,950 |
| 3 | On approval of Schematic Design | 27% | 292,950 |
| 4 | On approval of Design Development | 36% | 390,600 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to Northbeam Studio's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by Northbeam Studio; suspension rights for late payment; and termination on 30 days' written notice.

For and on behalf of Northbeam Studio

Northbeam Barcelona