Northbeam DESIGN

Northbeam Dubai

Fee Proposal

Arabian Sea Towers - twin residential towers, Mumbai

Prepared for: Arabian Sea Realty Pvt Ltd

Location: Mumbai, India

Reference: NBS-DXB-2025-033

Date: 2025-09-10

Validity: 90 days from the date of issue

# 1. Project Understanding

Arabian Sea Realty Pvt Ltd has invited Northbeam Studio to submit a fee proposal for Arabian Sea Towers - twin residential towers, Mumbai, located in Mumbai, India. The proposal covers Architecture, Interior Design services from Concept Design to Design Development.

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 1,184,029 sq ft |
| Site area | 102,257 sq ft |
| Interior design area | 48,438 sq ft |
| Residential units | 640 |
| Site considerations | Coastal regulation zone, tight plot, parking podium |

# 2. Scope of Services

## 2.1 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Schematic Design: Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

Design Development: Fully coordinated design development drawings; facade and envelope details; key interior architecture details; outline specifications; design development report to support the local architect of record.

## 2.2 Interior Design

Concept Design: Interior design concept and mood boards for public areas and key typical spaces; space planning; concept presentation.

Schematic Design: Developed layouts, reflected ceiling plans, key elevations and finishes palette; preliminary FF&E strategy.

Design Development: Detailed interior drawings for public areas and typical rooms or units; finishes schedule; FF&E design intent package.

# 3. Deliverables

- Design report and drawings per stage: 3

- Rendered images: 10

- Client presentations: 4

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Schematic Design | 8 weeks |
| Design Development | 12 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in INR and exclude VAT or other applicable taxes.

| Service | Stage | Fee (INR) |
| --- | --- | --- |
| Architecture | Concept Design | 51,800,000 |
| Architecture | Schematic Design | 51,800,000 |
| Architecture | Design Development | 69,100,000 |
| Interior Design | Concept Design | 2,100,000 |
| Interior Design | Schematic Design | 2,100,000 |
| Interior Design | Design Development | 2,800,000 |
|  | Total professional fee | 179,700,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (INR) | Amount (INR) |
| --- | --- | --- | --- |
| Rendered images | 10 | 130,000 | 1,300,000 |
| Site visits and meetings | 4 | 300,000 | 1,200,000 |

Marketing-quality still images

regional trip, 2 staff, flights, hotel, per diem

# 7. Payment Schedule

| No. | Milestone | Share | Amount (INR) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 17,970,000 |
| 2 | On approval of Concept Design | 27% | 48,519,000 |
| 3 | On approval of Schematic Design | 27% | 48,519,000 |
| 4 | On approval of Design Development | 36% | 64,692,000 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to Northbeam Studio's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by Northbeam Studio; suspension rights for late payment; and termination on 30 days' written notice.

## Client-requested amendments

| Clause | Client request | Northbeam position |
| --- | --- | --- |
| Liability cap | Uncapped liability | Cap at 100% of fee |

For and on behalf of Northbeam Studio

Northbeam Dubai