SOG DESIGN

SOG Dubai

Fee Proposal

Oasis Gardens - 120-villa community, Al Ain

Prepared for: Oasis Living Properties

Location: Al Ain, UAE

Reference: SOG-DXB-2023-031

Date: 2023-09-25

Validity: 90 days from the date of issue

# 1. Project Understanding

Oasis Living Properties has invited SOG Design to submit a fee proposal for Oasis Gardens - 120-villa community, Al Ain, located in Al Ain, UAE. The proposal covers Masterplanning, Architecture, Landscape Architecture services from Concept Design to Design Development.

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 48,000 m² |
| Site area | 32.0 ha |
| Landscape area | 95,000 m² |
| Residential units | 120 |
| Site considerations | Flat greenfield site |

SOG Design is pleased to continue its collaboration with Oasis Living Properties.

# 2. Scope of Services

## 2.1 Masterplanning

Concept Design: Masterplan concept: land-use plan, movement framework, open space network, phasing strategy and development controls; masterplan report.

Schematic Design: Refined masterplan with plot-level development parameters and design guidelines.

## 2.2 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Schematic Design: Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

Design Development: Fully coordinated design development drawings; facade and envelope details; key interior architecture details; outline specifications; design development report to support the local architect of record.

## 2.3 Landscape Architecture

Concept Design: Landscape concept and planting strategy; open space framework; hardscape and softscape character.

Schematic Design: Developed landscape plans; levels strategy; planting palette; water features and amenity areas.

Design Development: Coordinated landscape design development drawings; hardscape details; planting plans; irrigation design intent.

# 3. Deliverables

- Design report and drawings per stage: 3

- Rendered images: 12

- Client presentations: 4

- Masterplan framework report: 1

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Schematic Design | 8 weeks |
| Design Development | 12 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in AED and exclude VAT or other applicable taxes.

| Service | Stage | Fee (AED) |
| --- | --- | --- |
| Architecture | Concept Design | 1,890,000 |
| Architecture | Schematic Design | 1,890,000 |
| Architecture | Design Development | 2,520,000 |
| Landscape Architecture | Concept Design | 760,000 |
| Landscape Architecture | Schematic Design | 760,000 |
| Landscape Architecture | Design Development | 1,015,000 |
| Masterplanning | Concept Design | 940,000 |
| Masterplanning | Schematic Design | 535,000 |
|  | Total professional fee | 10,310,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (AED) | Amount (AED) |
| --- | --- | --- | --- |
| Rendered images | 12 | 7,500 | 90,000 |
| Site visits and meetings | 5 | 13,000 | 65,000 |

Marketing-quality still images

regional trip, 2 staff, flights, hotel, per diem

# 7. Payment Schedule

| No. | Milestone | Share | Amount (AED) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 1,031,000 |
| 2 | On approval of Concept Design | 31.3% | 3,227,030 |
| 3 | On approval of Schematic Design | 27.8% | 2,866,180 |
| 4 | On approval of Design Development | 30.9% | 3,185,790 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to SOG Design's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by SOG Design; suspension rights for late payment; and termination on 30 days' written notice.

For and on behalf of SOG Design

SOG Dubai