SOG DESIGN

SOG Ho Chi Minh City

Fee Proposal

Saigon Riverside One - mixed-use tower (residential, hotel, retail)

Prepared for: Saigon Riverside Land JSC

Location: Ho Chi Minh City, Vietnam

Reference: SOG-SGN-2024-011

Date: 2024-04-02

Validity: 90 days from the date of issue

# 1. Project Understanding

Saigon Riverside Land JSC has invited SOG Design to submit a fee proposal for Saigon Riverside One - mixed-use tower (residential, hotel, retail), located in Ho Chi Minh City, Vietnam. The proposal covers Architecture, Interior Design, Landscape Architecture services from Concept Design to GFC Review.

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 96,000 m² |
| Site area | 7,400 m² |
| Landscape area | 3,500 m² |
| Interior design area | 12,000 m² |
| Residential units | 380 |
| Hotel keys | 160 |
| Site considerations | Tight riverfront plot, three uses stacked, height-limit negotiation |

# 2. Scope of Services

## 2.1 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Schematic Design: Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

Basic Design / Design Development: Fully coordinated design development drawings; facade and envelope details; key interior architecture details; outline specifications; design development report to support the local architect of record.

GFC Review: Review of good-for-construction drawings prepared by the local architect of record for compliance with design intent; written comments and one follow-up review.

## 2.2 Interior Design

Concept Design: Interior design concept and mood boards for public areas and key typical spaces; space planning; concept presentation.

Schematic Design: Developed layouts, reflected ceiling plans, key elevations and finishes palette; preliminary FF&E strategy.

Basic Design / Design Development: Detailed interior drawings for public areas and typical rooms or units; finishes schedule; FF&E design intent package.

## 2.3 Landscape Architecture

Concept Design: Landscape concept and planting strategy; open space framework; hardscape and softscape character.

Schematic Design: Developed landscape plans; levels strategy; planting palette; water features and amenity areas.

Basic Design / Design Development: Coordinated landscape design development drawings; hardscape details; planting plans; irrigation design intent.

# 3. Deliverables

- Design report and drawings per stage: 4

- Rendered images: 14

- Client presentations: 5

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Schematic Design | 8 weeks |
| Basic Design / Design Development | 12 weeks |
| GFC Review | 6 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in USD and exclude VAT or other applicable taxes.

| Service | Stage | Fee (USD) |
| --- | --- | --- |
| Architecture | Concept Design | 831,500 |
| Architecture | Schematic Design | 831,500 |
| Architecture | Basic Design / Design Development | 1,109,000 |
| Architecture | GFC Review | 277,000 |
| Interior Design | Concept Design | 102,500 |
| Interior Design | Schematic Design | 102,500 |
| Interior Design | Basic Design / Design Development | 137,000 |
| Landscape Architecture | Concept Design | 5,700 |
| Landscape Architecture | Schematic Design | 5,700 |
| Landscape Architecture | Basic Design / Design Development | 7,600 |
|  | Total professional fee | 3,410,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (USD) | Amount (USD) |
| --- | --- | --- | --- |
| Rendered images | 14 | 1,500 | 21,000 |
| Site visits and meetings | 5 | 6,000 | 30,000 |

Marketing-quality still images

long haul trip, 2 staff, flights, hotel, per diem

# 7. Payment Schedule

| No. | Milestone | Share | Amount (USD) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 341,000 |
| 2 | On approval of Concept Design | 24.8% | 845,680 |
| 3 | On approval of Schematic Design | 24.8% | 845,680 |
| 4 | On approval of Design Development | 33.1% | 1,128,710 |
| 5 | On approval of GFC Review | 7.3% | 248,930 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to SOG Design's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by SOG Design; suspension rights for late payment; and termination on 30 days' written notice.

## Client-requested amendments

| Clause | Client request | SOG position |
| --- | --- | --- |
| Liability cap | Uncapped liability | Cap at 100% of fee |
| Payment terms | 90 days from invoice | 30 days from invoice |

For and on behalf of SOG Design

SOG Ho Chi Minh City