SOG DESIGN

SOG Guangzhou

Fee Proposal

Pearl Delta Tech HQ campus

Prepared for: Pearl Delta Technology Group

Location: Guangzhou, China

Reference: SOG-CAN-2023-008

Date: 2023-11-06

Validity: 90 days from the date of issue

# 1. Project Understanding

Pearl Delta Technology Group has invited SOG Design to submit a fee proposal for Pearl Delta Tech HQ campus, located in Guangzhou, China. The proposal covers Architecture, Landscape Architecture services from Concept Design to Preliminary Design (DD).

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 88,000 m² |
| Site area | 52,000 m² |
| Landscape area | 26,000 m² |
| Site considerations | Campus of four buildings with shared podium |

# 2. Scope of Services

## 2.1 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Schematic Design: Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

Preliminary Design (DD): Fully coordinated design development drawings; facade and envelope details; key interior architecture details; outline specifications; design development report to support the local architect of record.

## 2.2 Landscape Architecture

Concept Design: Landscape concept and planting strategy; open space framework; hardscape and softscape character.

Schematic Design: Developed landscape plans; levels strategy; planting palette; water features and amenity areas.

Preliminary Design (DD): Coordinated landscape design development drawings; hardscape details; planting plans; irrigation design intent.

# 3. Deliverables

- Design report and drawings per stage: 3

- Rendered images: 12

- Client presentations: 4

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Schematic Design | 8 weeks |
| Preliminary Design (DD) | 12 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in CNY and exclude VAT or other applicable taxes.

| Service | Stage | Fee (CNY) |
| --- | --- | --- |
| Architecture | Concept Design | 3,380,000 |
| Architecture | Schematic Design | 3,380,000 |
| Architecture | Preliminary Design (DD) | 4,510,000 |
| Landscape Architecture | Concept Design | 270,000 |
| Landscape Architecture | Schematic Design | 270,000 |
| Landscape Architecture | Preliminary Design (DD) | 360,000 |
|  | Total professional fee | 12,170,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (CNY) | Amount (CNY) |
| --- | --- | --- | --- |
| Rendered images | 12 | 11,000 | 132,000 |

Marketing-quality still images

# 7. Payment Schedule

| No. | Milestone | Share | Amount (CNY) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 1,217,000 |
| 2 | On approval of Concept Design | 27% | 3,285,900 |
| 3 | On approval of Schematic Design | 27% | 3,285,900 |
| 4 | On approval of Design Development | 36% | 4,381,200 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to SOG Design's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by SOG Design; suspension rights for late payment; and termination on 30 days' written notice.

For and on behalf of SOG Design

SOG Guangzhou