SOG DESIGN

SOG Dubai

Fee Proposal

Bay Square Offices - mid-rise office building

Prepared for: Marina Crest Developments LLC

Location: Dubai, UAE

Reference: SOG-DXB-2026-006

Date: 2026-03-04

Validity: 90 days from the date of issue

# 1. Project Understanding

Marina Crest Developments LLC has invited SOG Design to submit a fee proposal for Bay Square Offices - mid-rise office building, located in Dubai, UAE. The proposal covers Architecture, Interior Design services from Concept Design to Schematic Design.

| Item | Description |
| --- | --- |
| Gross floor area (GFA) | 27,000 m² |
| Site area | 3,600 m² |
| Interior design area | 9,000 m² |
| Site considerations | Regular plot in established business district |

SOG Design is pleased to continue its collaboration with Marina Crest Developments LLC.

# 2. Scope of Services

## 2.1 Architecture

Concept Design: Design vision and narrative; site planning and massing; plans, sections and elevations at concept level; outline area schedule; material palette; concept report and presentation.

Schematic Design: Development of the approved concept; coordinated plans, sections and elevations; facade strategy; preliminary coordination with structural and MEP consultants; updated area schedule; schematic design report.

## 2.2 Interior Design

Concept Design: Interior design concept and mood boards for public areas and key typical spaces; space planning; concept presentation.

Schematic Design: Developed layouts, reflected ceiling plans, key elevations and finishes palette; preliminary FF&E strategy.

# 3. Deliverables

- Design report and drawings per stage: 2

- Rendered images: 6

- Client presentations: 3

# 4. Programme

| Stage | Indicative duration |
| --- | --- |
| Concept Design | 8 weeks |
| Schematic Design | 8 weeks |

Durations exclude client review periods of two weeks per stage.

# 5. Fee Proposal

All fees are in AED and exclude VAT or other applicable taxes.

| Service | Stage | Fee (AED) |
| --- | --- | --- |
| Architecture | Concept Design | 735,000 |
| Architecture | Schematic Design | 735,000 |
| Interior Design | Concept Design | 165,000 |
| Interior Design | Schematic Design | 165,000 |
|  | Total professional fee | 1,800,000 |

# 6. Reimbursable Expenses

| Item | Quantity | Unit rate (AED) | Amount (AED) |
| --- | --- | --- | --- |
| Rendered images | 6 | 7,500 | 45,000 |

Marketing-quality still images

# 7. Payment Schedule

| No. | Milestone | Share | Amount (AED) |
| --- | --- | --- | --- |
| 1 | Advance on signing | 10% | 180,000 |
| 2 | On approval of Concept Design | 45% | 810,000 |
| 3 | On approval of Schematic Design | 45% | 810,000 |

Invoices are payable within 30 days of issue.

# 8. Exclusions

- Structural, MEP and civil engineering design

- Local architect of record and authority submissions

- Construction documentation and tender documents

- Site supervision and contract administration

- Surveys, geotechnical investigations and specialist consultants

- Physical models

# 9. Terms and Conditions

This proposal is subject to SOG Design's Standard Terms of Engagement (version 2023.1), including: two rounds of design revisions per stage; liability limited to 100% of the professional fee; copyright in the design retained by SOG Design; suspension rights for late payment; and termination on 30 days' written notice.

For and on behalf of SOG Design

SOG Dubai